## Sheet1
program | build | qty. | config. | cmbuild | buykit | status | cm | fabturnship | pcbfabout | absrdue | buildstart | pcafirst-offandormechasystart | buildfinish | testrequirements | buildnotes | chipvers. | materialsnotes | pm | hw | npieelec. | diags | mech.de | npiemech. | scmm | mfg.Test Eng | family
Bearpaw | P2A | 19 | N\A | ASY-54270-102 | ASY-54270-102 | In-Process | SSJ | 17 | 1/21/20 | 2/14/20 | 2/21/20 | 2/28/20 | 3/20/20 | AOI,5DX,FP,FVT | N\A | B1 | N\A | Poornima | Linda F. | James M. | John Jiang | Kash | Rohit K. | Attiya | Min Guo | Denali
Bearpaw | P2B | 45 | N\A | ASY-54270-102 | ASY-54270-102 | Not Started | SSJ | 15 | 1/21/20 | 3/13/20 | 3/20/20 | 3/27/20 | 4/17/20 | AOI,5DX,FP,FVT,ESS,BI,FST | 11/8: Added 15 boards from P1B | B1 | N\A | Poornima | Linda F. | James M. | John Jiang | Kash | Rohit K. | Attiya | Min Guo | Denali
Bearpaw | PLT | 50 | N\A | ASY-54270-102 | ASY-54270-102 | Not Started | SGD | 15 | 5/11/20 | 7/1/20 | 7/8/20 | 7/15/20 | 8/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Poornima | Linda F. | James M. | John Jiang | Kash | Rohit K. | Attiya | Min Guo | Denali
Bearpaw | PPLT | 30 | N\A | ASY-54270-102 | ASY-54270-102 | Not Started | SGD | 15 | 5/11/20 | 6/1/20 | 6/8/20 | 6/15/20 | 7/6/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | N\A | B1 | N\A | Poornima | Linda F. | James M. | John Jiang | Kash | Rohit K. | Attiya | Min Guo | Denali
Bearpaw (Mezz Card) | P2A | 0 | N\A | PCA-01431-02 | PCA-01431-02 | Not Started | SSJ | 15 | 3/6/20 | 3/17/20 | 3/24/20 | 3/31/20 | 4/21/20 | AOI,5DX,FP | For Bearpaw P2A and P1B QTY :25 | B1 | N\A | Poornima | Linda F. | James M. | John Jiang | Kash | Rohit K. | Attiya | Min Guo | Denali
Bearpaw (Mezz Card) | P2B | 0 | N\A | PCA-01431-02 | PCA-01431-02 | Not Started | SSJ | 15 | 3/4/20 | 4/3/20 | 4/10/20 | 4/17/20 | N\A | AOI,5DX,FP | For Bearpaw P2B QTY : 45 | N\A | N\A | UNK | N\A | N\A | N\A | N\A | N\A | N\A | UNK | UNK
Bird Island | TQA | 5 | no SSD,PSU,fan | ASY-72018-120 | ASY-72018-120 | Not Started | SGD | 0 | N\A | 4/9/20 | 4/16/20 | 4/30/20 | 5/14/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | N\A | Juan | John H. |  | Jack | PoE
Bird Island | TQA | 25 | Forward | ASY-92026-120 | ASY-92026-120 | Not Started | SGD | 0 | N\A | 4/9/20 | 4/16/20 | 4/30/20 | 5/14/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | N\A | Juan | John H. |  | Jack | PoE
Bird Island | TQB | 10 | no SSD,PSU,fan | ASY-72018-120 | ASY-72018-120 | Not Started | SGD | 0 | N\A | 5/11/20 | 5/18/20 | 6/1/20 | 6/15/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | N\A | Juan | John H. |  | Jack | PoE
Bird Island | TQB | 90 | Forward | ASY-92026-120 | ASY-92026-120 | Not Started | SGD | 0 | N\A | 5/11/20 | 5/18/20 | 6/1/20 | 6/15/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | N\A | Juan | John H. |  | Jack | PoE
BLACK DIAMOND 16 | Build 1 | 20 | N\A | ASY-02698-01 | ASY-02698-01 | In-Process | SSJ | 20 | N\A | N\A | 2/28/20 | N\A | N\A | N\A | (2019-11-26) Add to Forecast for SSJ | N\A | N\A | Tim | N\A | N\A | N\A | N\A | N\A | Tim | UNK | ALBRIGHT Loopback Test Board
BLACK DIAMOND 16 | Build 2 | 110 | N\A | ASY-02698-01 | ASY-02698-01 | Not Started | SSJ | 110 | N\A | N\A | 4/10/20 | N\A | N\A | N\A | (2020-02-04) QTY 60 to JPE (2020-02-04) QTY 50 to SGD (2020-02-04) Add to Forecast for SSJ | N\A | N\A | Tim | N\A | N\A | N\A | N\A | N\A | Tim | UNK | ALBRIGHT Loopback Test Board
Brooks | PLT | 129 | N\A | ASY-53924-109 | ASY-53924-109 | Not Started | SGD | 15 | 11/22/19 | 3/10/20 | 3/17/20 | 3/24/20 | 4/14/20 | AOI,5DX,FP,FVT,ESS,BI,FST | N\A | B0 | N\A | Mike M. | Andrew | James M. | TBD | Matt G. | M. Lee | Attiya | Min Guo | Denali
Brooks | PLT | 200 | N\A | ASY-53924-109 | ASY-53924-109 | Not Started | SGD | 15 | 11/22/19 | 4/9/20 | 4/16/20 | 4/23/20 | 5/14/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 5/7: Qty 24 for DF | B0 | N\A | Mike M. | Andrew | James M. | TBD | Matt G. | M. Lee | Attiya | Min Guo | Denali
Brooks | PPLT-1 | 20 | N\A | ASY-53924-109 | ASY-53924-109 | In-Process | SGD | 15 | 11/22/19 | 2/7/20 | 2/14/20 | 2/21/20 | 3/13/20 | AOI,5DX,FP,FVT,ESS,BI,FST | N\A | B0 | N\A | Mike M. | Andrew | James M. | TBD | Matt G. | M. Lee | Attiya | Min Guo | Denali
Brooks Island | TQA | 5 | no SSD,PSU,fan | ASY-72004-110 | ASY-72004-110 | Not Started | SGD | 0 | N\A | 4/1/20 | 4/8/20 | 4/22/20 | 5/6/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | Dilip | Juan | John H. |  | Jack | PoE
Brooks Island | TQA | 25 | Forward | ASY-92006-110 | ASY-92006-110 | Not Started | SGD | 0 | N\A | 4/1/20 | 4/8/20 | 4/22/20 | 5/6/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | Dilip | Juan | John H. |  | Jack | PoE
Brooks Island | TQB | 10 | W/SSD. No PSU,fan | ASY-72004-110 | ASY-72004-110 | Not Started | SGD | 0 | N\A | 4/29/20 | 5/8/20 | 5/22/20 | 6/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | Dilip | Juan | John H. |  | Jack | PoE
Brooks Island | TQB | 90 | Forward | ASY-92006-110 | ASY-92006-110 | Not Started | SGD | 0 | N\A | 4/29/20 | 5/8/20 | 5/22/20 | 6/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Larry | Shashi T. | Welson C. | Dilip | Juan | John H. |  | Jack | PoE
Clearwater | PLT | 110 | N\A | ASY-53055-108 | ASY-53055-108 | In-Process | SGD | 15 | 9/11/19 | 2/3/20 | 2/10/20 | 2/17/20 | 3/9/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 5/7: Qty 4 for the DF (BCM88690, IC-00856-04) | B1 | IC-00856-04 | Mike M. | David A. | Nam N. | Michael Chan | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Clearwater MS | PLT | 120 | N\A | ASY-53242-105 | ASY-53242-105 | In-Process | SGD | 15 | 7/31/19 | 12/16/19 | 12/23/19 | 12/30/19 | 1/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | IC-00856-04 | Mike M. | Eddie A. | Nam N. | TBD | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Clearwater MS | PPLT-1 | 2 | N\A | ASY-53242-110 | ASY-53242-110 | In-Process | SGD | 15 | 7/31/19 | 9/10/19 | 9/17/19 | 9/24/19 | 10/15/19 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | 1/2 MDB (BCM88694) | B1 | IC-00856-04 | Mike M. | Eddie A. | Nam N. | TBD | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Clearwater MS | PPLT-1 | 60 | N\A | ASY-53242-104 | ASY-53242-104 | In-Process | SGD | 15 | 7/31/19 | 9/10/19 | 9/17/19 | 9/24/19 | 10/15/19 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | BCM88690 | B1 | IC-00856-04 | Mike M. | Eddie A. | Nam N. | TBD | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Clearwater MS | PPLT-2 | 15 | N\A | ASY-53242-106 | ASY-53242-106 | In-Process | SGD | 31 | 9/27/19 | 11/12/19 | 11/19/19 | 11/26/19 | 12/17/19 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | BCM88690. Build 10 with ISU and 5 with GCE | B1 | IC-00856-04 | Mike M. | Eddie A. | Nam N. | TBD | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Clearwater MS-2 | P1A | 11 | N\A | ASY-53058-101 | ASY-53058-101 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 | P1B | 16 | N\A | ASY-53058-101 | ASY-53058-101 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 | P2A | 20 | N\A | ASY-53058-102 | ASY-53058-102 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 | P2B | 40 | N\A | ASY-53058-102 | ASY-53058-102 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 | PLT | 40 | N\A | ASY-53058-103 | ASY-53058-103 | Not Started | SGD | 15 | 6/22/20 | 8/12/20 | 8/19/20 | 8/26/20 | 9/16/20 | AOI,5DX,ICT, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 | PPLT | 40 | N\A | ASY-53058-103 | ASY-53058-103 | Not Started | SGD | 15 | 6/22/20 | 7/13/20 | 7/20/20 | 7/27/20 | 8/17/20 | AOI,5DX,ICT, FVT, ESS, BI, FST, ORT | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 Riser Card | P1A | 0 | N\A | PCA-01515-01 | PCA-01515-01 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | Qty = 143 +75 = 218 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 Riser Card | P1B | 0 | N\A | PCA-01515-01 | PCA-01515-01 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 208 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 Riser Card | P2A | 0 | N\A | PCA-01515-02 | PCA-01515-02 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 260 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater MS-2 Riser Card | P2B | 0 | N\A | PCA-01515-02 | PCA-01515-02 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 520 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | P1A | 11 | N\A | ASY-55091-101 | ASY-55091-101 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | P1B | 16 | N\A | ASY-55091-101 | ASY-55091-101 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | P2A | 20 | N\A | ASY-55091-102 | ASY-55091-102 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | P2B | 40 | N\A | ASY-55091-102 | ASY-55091-102 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | PLT | 40 | N\A | ASY-55091-103 | ASY-55091-103 | Not Started | SGD | 15 | 6/22/20 | 8/12/20 | 8/19/20 | 8/26/20 | 9/16/20 | AOI,5DX,ICT, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 | PPLT | 40 | N\A | ASY-55091-103 | ASY-55091-103 | Not Started | SGD | 15 | 6/22/20 | 7/13/20 | 7/20/20 | 7/27/20 | 8/17/20 | AOI,5DX,ICT, FVT, ESS, BI, FST, ORT | N\A | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 Riser Card | P1A | 0 | N\A | PCA-01510-01 | PCA-01510-01 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | Qty = 143 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 Riser Card | P1B | 0 | N\A | PCA-01510-01 | PCA-01510-01 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 208 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 Riser Card | P2A | 0 | N\A | PCA-01510-02 | PCA-01510-02 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 260 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-2 Riser Card | P2B | 0 | N\A | PCA-01510-02 | PCA-01510-02 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 520 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Julie | Min Guo | Denali
Clearwater-BK | PLT | 30 | N\A | ASY-54701-102 | ASY-54701-102 | In-Process | SGD | 15 | 4/12/19 | 2/3/20 | 2/10/20 | 2/17/20 | 3/9/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | BK (BCM88690, IC-00856-04) | B1 | IC-01105-01 | Mike M. | David A. | Nam N. | Michael Chan | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Dall | P1A | 8 | N\A | ASY-54634-101 | ASY-54634-101 | Not Started | SSJ | 15 | 3/16/20 | 4/8/20 | 4/15/20 | 4/22/20 | 5/13/20 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dall | P1B | 57 | N\A | ASY-54634-101 | ASY-54634-101 | Not Started | SSJ | 15 | 3/16/20 | 5/8/20 | 5/15/20 | 5/22/20 | 6/12/20 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dall | P2A | 70 | N\A | ASY-54634-102 | ASY-54634-102 | Not Started | SSJ | 15 | 8/17/20 | 9/8/20 | 9/15/20 | 9/22/20 | 10/13/20 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dall | P2B | 70 | N\A | ASY-54634-102 | ASY-54634-102 | Not Started | SSJ | 15 | 8/17/20 | 10/8/20 | 10/15/20 | 10/22/20 | 11/12/20 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dall | PLT | 130 | N\A | ASY-54634-103 | ASY-54634-103 | Not Started | SGD | 15 | 12/18/20 | 2/12/21 | 2/19/21 | 2/26/21 | 3/19/21 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dall | PPLT | 110 | N\A | ASY-54634-103 | ASY-54634-103 | Not Started | SGD | 15 | 12/18/20 | 1/13/21 | 1/20/21 | 1/27/21 | 2/17/21 | AOI,5DX,FP | N\A | N\A | N\A | Poornima | Istvan | James M. | TBD | Matt G. | Rohit K. | Attiya | TBD | Denali
Dragonfly | P1A | 28 | N\A | ASY-54997-101 | ASY-54997-101 | Not Started | SSJ | 15 | 3/6/20 | 3/27/20 | 4/3/20 | 4/8/20 | 5/1/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Dragonfly | P1B | 40 | N\A | ASY-54997-101 | ASY-54997-101 | Not Started | SSJ | 15 | 3/6/20 | 4/27/20 | 5/3/20 | 5/6/20 | 5/29/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Dragonfly | P2A | 78 | N\A | ASY-54997-102 | ASY-54997-102 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/10/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Dragonfly | P2B | 55 | N\A | ASY-54997-102 | ASY-54997-102 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/8/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Dragonfly | PLT | 100 | N\A | ASY-54997-103 | ASY-54997-103 | Not Started | SGD | 15 | 6/22/20 | 8/12/20 | 8/19/20 | 8/24/20 | 9/16/20 | AOI,5DX,FP, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Dragonfly | PPLT | 64 | N\A | ASY-54997-103 | ASY-54997-103 | Not Started | SGD | 15 | 6/22/20 | 7/13/20 | 7/20/20 | 7/23/20 | 8/17/20 | AOI,5DX,FP, FVT, ESS, BI, ORT, FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min | Denali
Eldridge | PLT-1 | 99 | N\A | ASY-53061-112 | ASY-53061-112 | In-Process | SSJ | 15 | 7/25/19 | 12/20/19 | 12/27/19 | 1/3/20 | 1/24/20 | AOI,5DX,ICT, FP,FVT,ESS, BI, FST | N\A | B0 | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Eldridge | PLT-2 | 100 | N\A | ASY-53061-112 | ASY-53061-112 | In-Process | SGD | 15 | 7/25/19 | 1/7/20 | 1/14/20 | 1/21/20 | 2/11/20 | AOI,5DX,ICT, FP,FVT,ESS, BI, FST | N\A | B0 | N\A | Mike M. | Paulmer | James M. | Mike R. | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Eldridge-S | P1B | 78 | N\A | ASY-54482-104 | ASY-54482-104 | In-Process | SSJ | 30 | 5/31/19 | 10/3/19 | 10/10/19 | 10/15/19 | 11/7/19 | AOI,5DX,FP,FVT | 8/6: Added 38 from P1A | B0 | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | UNK | Denali
Eldridge-S | P2A | 52 | N\A | ASY-54482-105 | ASY-54482-105 | Not Started | SSJ | 30 | 3/23/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP,FVT | N\A | B0 | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | UNK | Denali
Eldridge-S | P2B | 64 | N\A | ASY-54482-105 | ASY-54482-105 | Not Started | SSJ | 30 | 3/23/20 | 5/22/20 | 5/29/20 | 6/5/20 | 6/26/20 | AOI,5DX,FP,FVT | N\A | B0 | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | UNK | Denali
Eldridge-S | PLT | 124 | N\A | ASY-54482-105 | ASY-54482-105 | Not Started | SGD | 30 | 8/3/20 | 10/16/20 | 10/23/20 | 10/30/20 | 11/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B0 | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | UNK | Denali
Eldridge-S | PPLT | 112 | N\A | ASY-54482-105 | ASY-54482-105 | Not Started | SGD | 30 | 8/3/20 | 9/16/20 | 9/23/20 | 9/30/20 | 10/21/20 | AOI,5DX,ICT,FVT,ESS,BI,FST, ORT | N\A | B0 | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | UNK | Denali
Hedgehog | P1A | 0 | N\A | ASY-05091-01 | ASY-05091-01 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | QTY = 41 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Hedgehog | P1B | 0 | N\A | ASY-05091-01 | ASY-05091-01 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | QTY = 71 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Hedgehog | P2A | 0 | N\A | ASY-05091-02 | ASY-05091-02 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | QTY = 79 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Hedgehog | P2B | 0 | N\A | ASY-05091-02 | ASY-05091-02 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, FVT, ESS, BI | QTY = 176 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Hedgehog Riser Card | P1A | 0 | N\A | PCA-01513-01 | PCA-01513-01 | Not Started | SSJ | 15 | 3/16/20 | 4/7/20 | 4/14/20 | 4/21/20 | 5/12/20 | AOI,5DX,FP | QTY = 112 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Hedgehog Riser Card | P1B | 0 | N\A | PCA-01513-01 | PCA-01513-01 | Not Started | SSJ | 15 | 3/16/20 | 5/7/20 | 5/14/20 | 5/21/20 | 6/11/20 | AOI,5DX,FP, FVT, ESS, BI | QTY = 255 | N\A | N\A | Mike M. | Xiaoping | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Horseshoe Lake | P2A | 8 | N\A | ASY-53984-102 | ASY-53984-102 | Not Started | SSJ | 15 | 3/23/20 | 4/15/20 | 4/22/20 | 4/29/20 | 5/20/20 | AOI,5DX,FP,FVT | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Horseshoe Lake | P2B | 20 | N\A | ASY-53984-102 | ASY-53984-102 | Not Started | SSJ | 15 | 3/23/20 | 5/15/20 | 5/22/20 | 5/29/20 | 6/19/20 | AOI,5DX,FP,FVT,ESS,BI,FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Horseshoe Lake | PLT | 15 | N\A | ASY-53984-102 | ASY-53984-102 | Not Started | SGD | 15 | 8/3/20 | 10/8/20 | 10/15/20 | 10/22/20 | 11/12/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Horseshoe Lake | PPLT | 20 | N\A | ASY-53984-102 | ASY-53984-102 | Not Started | SGD | 15 | 8/3/20 | 8/24/20 | 8/31/20 | 9/7/20 | 9/28/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Horseshoe Lake Test Chassis | P4A | 15 | N\A | ASY-04122-04 | ASY-04122-04 | Not Started | SSJ | 15 | 3/23/20 | 4/6/20 | 4/15/20 | 4/22/20 | 5/14/20 | AOI,5DX,FP | 1/06: Need to update PN to -05 when available 9/25: Updated PN to ASY-04122-03, ECO 12273 Released | N\A | N\A | Kathi E. | Pranav | James M. | Nguyen L. | TK Soo | Rohit K. | Attiya | Min Guo | Denali
Lorikeet-SSJ | P2B | 0 | PCA only | PCA-01392-02 | PCA-01392-02 | Not Started | SSJ | 15 | 2/10/20 | 2/25/20 | 3/3/20 | 3/6/20 | 3/13/20 | AOI,5DX,FLY | 2/10: Qty. 8 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Lorikeet-SSJ | P2C | 0 | PCA only | PCA-01392-02 | PCA-01392-02 | Not Started | SSJ | 0 | N\A | 3/25/20 | 4/1/20 | 4/8/20 | 4/24/20 | AOI,5DX,FLY | 2/10: Qty. 16 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Lorikeet-SSJ | P2C | 0 | PCA only | PCA-01392-02 | PCA-01392-02 | Not Started | SSJ | 0 | N\A | 7/8/20 | 7/15/20 | 7/22/20 | 8/5/20 | AOI,5DX,FLY | 2/10: Qty. 28 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Lorikeet-SSJ | P2C | 0 | PCA only | PCA-01392-02 | PCA-01392-02 | Not Started | SSJ | 15 | 5/18/20 | 6/2/20 | 6/9/20 | 6/16/20 | 6/26/20 | AOI,5DX,FLY | 2/10: Qty. 22 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Marysville | TQA | 5 | no SSD,PSU,fan | ASY-71999-110 | ASY-71999-110 | In-Process | SGD | 0 | 11/27/19 | 12/25/19 | 1/1/20 | 1/15/20 | 1/29/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
Marysville | TQA | 10 | Reverse | ASY-92003-110 | ASY-92003-110 | In-Process | SGD | 0 | 11/27/19 | 12/25/19 | 1/1/20 | 1/15/20 | 1/29/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
Marysville | TQA | 15 | Forward | ASY-92002-110 | ASY-92002-110 | In-Process | SGD | 0 | 11/27/19 | 12/25/19 | 1/1/20 | 1/15/20 | 1/29/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 4/29- Mgt requested to move TQ build to early Q4 due to SGD capacity 10/9- Decided to wait for 2 piece metal build (10/11->11/8). Tooling takes 4 weeks, 20 Trend, 10 Interplex) 11/19- SMT moved out 1 week waiting A0 release- Diags script rediness | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
Marysville | TQB | 10 | no SSD,PSU,fan | ASY-71999-110 | ASY-71999-110 | In-Process | SGD | 0 | 1/20/20 | 2/17/20 | 2/24/20 | 3/9/20 | 3/23/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
Marysville | TQB | 20 | Reverse | ASY-92003-110 | ASY-92003-110 | In-Process | SGD | 0 | 1/20/20 | 2/17/20 | 2/24/20 | 3/9/20 | 3/23/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
Marysville | TQB | 70 | Forward | ASY-92002-110 | ASY-92002-110 | In-Process | SGD | 0 | 1/20/20 | 2/17/20 | 2/24/20 | 3/9/20 | 3/23/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 1/16- TQB moved out from 1/16 to 1/28. No 2 piece metall order late december. Materials issue. | A0 | Yuba | FeliciaY | Aravind M | Anthony R. | Dilip | Crystal | Matt M. |  | Anand | 1RU
McKinley | PLT | 34 | N\A | ASY-53052-109 | ASY-53052-109 | Not Started | SGD | 15 | 11/15/19 | 3/10/20 | 3/17/20 | 3/24/20 | 4/14/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Mike M. | Aravind | Nick D. | Nguyen Le | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
McKinley | PPLT-2A | 10 | N\A | ASY-53052-108 | ASY-53052-108 | In-Process | SGD | 15 | 9/18/19 | 12/5/19 | 12/12/19 | 12/19/19 | 1/9/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Mike M. | Aravind | Nick D. | Nguyen Le | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
McKinley | PPLT-2B | 34 | N\A | ASY-53052-109 | ASY-53052-109 | In-Process | SGD | 15 | 9/18/19 | 1/24/20 | 1/31/20 | 2/7/20 | 2/28/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Mike M. | Aravind | Nick D. | Nguyen Le | Matt G. | Rohit K. | Lorraine | Min Guo | Denali
Montebello system | PLT | 4 | no SSD,PSU,fan | ASY-72017-102 | ASY-72017-102 | Not Started | SGD | 0 | N\A | 4/13/20 | 4/20/20 | 4/30/20 | 5/19/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
Montebello system | PLT | 6 | Reverse | ASY-92025-102 | ASY-92025-102 | Not Started | SGD | 0 | N\A | 4/13/20 | 4/20/20 | 4/30/20 | 5/19/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
Montebello system | PLT | 40 | Forward | ASY-92024-102 | ASY-92024-102 | Not Started | SGD | 0 | 3/10/20 | 4/13/20 | 4/20/20 | 4/30/20 | 5/19/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
Montebello system | PPLT | 2 | no SSD,PSU,fan | ASY-72017-102 | ASY-72017-102 | Not Started | SGD | 0 | N\A | 3/10/20 | 3/18/20 | 3/30/20 | 4/13/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
Montebello system | PPLT | 2 | Reverse | ASY-92025-102 | ASY-92025-102 | Not Started | SGD | 0 | N\A | 3/10/20 | 3/18/20 | 3/30/20 | 4/17/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
Montebello system | PPLT | 6 | Forward | ASY-92024-102 | ASY-92024-102 | Not Started | SGD | 0 | N\A | 3/10/20 | 3/18/20 | 3/30/20 | 4/13/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 2/27: Moved start date out from 2/28 to 3/18, but actual date is TBD. 2/20: Build start now TBD because parts were given to Torrance PPLT. Issue with parts from China. Best start date TBD. 1/20/20: PPLT Start date moved out from 1/28 to 2/12 due to SMT fixtures and mech asy fixtures not yet ordered. 12/16: Moved built start out from 1/9 to 1/19. | A1 | N\A | Madeleine | Brijesh, Xiaoping | Duong N. | Srini | Cliff | Michael L. | Lorraine | Sherry | 2RU
OSFP LED PCB (McKinley) | PPLT-2 | 0 | N\A | PCA-01191-01 | PCA-01191-01 | Not Started | SGD | 15 | 8/23/19 | 12/5/19 | 12/12/19 | 12/19/19 | 1/9/20 | AOI,5DX,FP,FVT,ESS,BI,FST | Build Qty = 135 | N\A | N\A | Mike M. | Aravind | Nick D. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake | PLT | 70 | N\A | ASY-53247-107 | ASY-53247-107 | In-Process | SGD | 25 | 3/29/19 | 12/4/19 | 12/11/19 | 12/18/19 | 1/8/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 5/7: 8 SUPs for DF & 50 for Camp | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake Test Chassis | P3B | 30 | N\A | ASY-03967-04 | ASY-03967-04 | In-Process | SSJ | 0 | N\A | 2/6/20 | 2/13/20 | 2/21/20 | 3/13/20 | AOI,5DX,FP,FVTc | 2/13: SMT Started | N\A | N\A | Kathi E. | Pranav | James M. | Nguyen L. | TK Soo | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | P1A | 16 | N\A | ASY-55228-101 | ASY-55228-101 | Not Started | SSJ | 15 | 2/20/20 | 3/12/20 | 3/19/20 | 3/26/20 | 4/16/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | P1B | 17 | N\A | ASY-55228-101 | ASY-55228-101 | Not Started | SSJ | 15 | 2/20/20 | 4/13/20 | 4/18/20 | 4/24/20 | 5/15/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | P2A | 24 | N\A | ASY-55228-102 | ASY-55228-102 | Not Started | SSJ | 15 | 5/8/20 | 5/29/20 | 6/5/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, ICT, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | P2B | 21 | N\A | ASY-55228-102 | ASY-55228-102 | Not Started | SSJ | 15 | 5/8/20 | 6/29/20 | 7/5/20 | 7/10/20 | 7/31/20 | AOI,5DX,FP, ICT, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | PLT | 40 | N\A | ASY-55228-103 | ASY-55228-103 | Not Started | SGD | 15 | 6/22/20 | 8/12/20 | 8/19/20 | 8/26/20 | 9/16/20 | AOI,5DX, ICT, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Otter Lake-2 | PPLT | 16 | N\A | ASY-55228-103 | ASY-55228-103 | Not Started | SGD | 15 | 6/22/20 | 7/13/20 | 7/20/20 | 7/27/20 | 8/17/20 | AOI,5DX, ICT, FVT, ESS, BI, ORT, FST | N\A | N\A | N\A | Mike M. | Paulmer | James M. | Nguyen Le | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Redwood | PLT | 100 |  | ASY-52976-105 | ASY-52976-105 | On Hold | SGD | 23 | 3/30/20 | 4/27/20 | 5/4/20 | 5/18/20 | 6/1/20 | AOI,5DX,ICT,FVT, ESS, BI, FST | 11/12: Pushed build start from 11/18 to 11/25 based on pending ECO's & PPLT delays 7/23: Revised SMT start date to 10/8 due to PPLT fab spin 7/16: Build placed on hold pending decision to spin fab to resolve functional issue | N\A | N\A | Sean | John G | James M | Harold | Victor | Rohit | Julie | Anand | Sequoia
Silverthrone-MO (Riser Card) | PLT | 0 | N\A | PCA-01308-02 | PCA-01308-02 | Not Started | SGD | 15 | 8/7/20 | 9/28/20 | 10/3/20 | 10/9/20 | 10/30/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | Qty = 720 | B1 | N\A | Mike M. | Aravind | Welson Chan | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MO (Riser Card) | PPLT | 0 | N\A | PCA-01308-02 | PCA-01308-02 | Not Started | SGD | 15 | 8/7/20 | 8/27/20 | 9/3/20 | 9/10/20 | 10/1/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | Qty = 396 | B1 | N\A | Mike M. | Aravind | Welson Chan | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ | P2A | 8 | N\A | ASY-53988-102 | ASY-53988-102 | Not Started | SSJ | 15 | 3/11/20 | 4/1/20 | 4/8/20 | 4/15/20 | 5/6/20 | AOI,5DX,FP,FVT | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ | P2B | 53 | N\A | ASY-53988-102 | ASY-53988-102 | Not Started | SSJ | 15 | 3/11/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP,FVT,ESS,BI,FST | 3/3: Increased from 33 to 53 for Skyline | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ | PLT | 40 | N\A | ASY-53988-102 | ASY-53988-102 | Not Started | SGD | 15 | 5/11/20 | 7/1/20 | 7/8/20 | 7/15/20 | 8/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ | PPLT | 22 | N\A | ASY-53988-102 | ASY-53988-102 | Not Started | SGD | 15 | 5/11/20 | 6/1/20 | 6/8/20 | 6/15/20 | 7/6/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ (Riser Card) | P1B | 0 | N\A | PCA-01310-01 | PCA-01310-01 | In-Process | SSJ | 15 | 8/23/19 | 2/25/20 | 3/3/20 | 3/10/20 | 3/31/20 | AOI,5DX,FP | Qty = 64 | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ (Riser Card) | P3A | 0 | N\A | PCA-01310-02 | PCA-01310-02 | Not Started | SSJ | 15 | 3/12/20 | 4/6/20 | 4/13/20 | 4/20/20 | 5/11/20 | AOI,5DX,FP,FVT | Qty = 152 | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ (Riser Card) | P3B | 0 | N\A | PCA-01310-02 | PCA-01310-02 | Not Started | SSJ | 15 | 3/12/20 | 5/6/20 | 5/13/20 | 5/20/20 | 6/10/20 | AOI,5DX,FP,FVT,ESS,BI,FST | Qty = 1000 | B1 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ (Riser Card) | PLT | 0 | N\A | PCA-01310-02 | PCA-01310-02 | Not Started | SGD | 15 | 5/11/20 | 7/1/20 | 7/8/20 | 7/15/20 | 8/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | Qty = 720 | B1 | N\A | Mike M. | Aravind | Welson Chan | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-MQ (Riser Card) | PPLT | 0 | N\A | PCA-01310-02 | PCA-01310-02 | Not Started | SGD | 15 | 5/11/20 | 6/1/20 | 6/8/20 | 6/15/20 | 7/6/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | Qty = 396 | B1 | N\A | Mike M. | Aravind | Welson Chan | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-O | P1A | 5 | N\A | ASY-55195-101 | ASY-55195-101 | Not Started | SSJ | 15 | 3/11/20 | 4/1/20 | 4/8/20 | 4/15/20 | 5/6/20 | AOI,5DX,FP | 3 x J2 (will be P2 fab) | A0 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-O (Riser Card) | P1A | 0 | N\A | PCA-01508-01 | PCA-01508-01 | Not Started | SSJ | 15 | 2/25/20 | 3/17/20 | 3/24/20 | 3/31/20 | 4/21/20 | AOI,5DX,FP | Qty = 155 | A0 | N\A | Mike M. | Aravind | Welson C. | Michael C. | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q | P1C | 20 | N\A | ASY-53987-102 | ASY-53987-102 | In-Process | SSJ | 15 | 4/24/19 | 10/17/19 | 10/24/19 | 10/31/19 | 11/21/19 | AOI,5DX,FP | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q | P2A | 12 | N\A | ASY-53987-102 | ASY-53987-102 | Not Started | SSJ | 15 | 3/11/20 | 4/1/20 | 4/8/20 | 4/15/20 | 5/6/20 | AOI,5DX,FP,FVT | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q | P2B | 53 | N\A | ASY-53987-102 | ASY-53987-102 | Not Started | SSJ | 15 | 3/11/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP,FVT,ESS,BI,FST | 3/3: Increased from 33 to 53 for Skyline | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q | PLT | 40 | N\A | ASY-53987-102 | ASY-53987-102 | Not Started | SGD | 15 | 5/11/20 | 7/1/20 | 7/8/20 | 7/15/20 | 8/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q | PPLT | 34 | N\A | ASY-53987-102 | ASY-53987-102 | Not Started | SGD | 15 | 5/11/20 | 6/1/20 | 6/8/20 | 6/15/20 | 7/6/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | N\A | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q (Riser Card) | P3A | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SSJ | 15 | 2/25/20 | 3/17/20 | 3/24/20 | 3/31/20 | 4/21/20 | AOI,5DX,FP | Qty = 240, P3A RC for Silverthrone-Q P2A & CW-2 P1A | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q (Riser Card) | P3B | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SSJ | 15 | 2/25/20 | 4/16/20 | 4/23/20 | 4/30/20 | 5/21/20 | AOI,5DX,FP,FVT | Qty = 1000, P3B Riser Card for Silverthrone-Q P2B | B1 | N\A | Mike M. | Aravind | Welson C. | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q (Riser Card) | PLT | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SGD | 15 | 5/11/20 | 7/1/20 | 7/8/20 | 7/15/20 | 8/5/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | Qty = 720 | B1 | N\A | Mike M. | Aravind | Welson Chan | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
Silverthrone-Q (Riser Card) | PPLT | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SGD | 15 | 5/11/20 | 6/1/20 | 6/8/20 | 6/15/20 | 7/6/20 | AOI,5DX,ICT,FVT,ESS,BI,ORT,FST | Qty = 612 | B1 | N\A | Mike M. | Aravind | Welson Chan | Yi Zou | Kash | Rohit K. | Attiya | Min Guo | Denali
THOR Chassis | P1A | 10 | N\A | ASY-O5235-01 | ASY-05235-01 | Not Started | SSJ | 10 | N\A | 4/1/20 | 4/9/20 | 4/15/20 | 4/20/20 | TBD | Fixture and assembly instructions required; Developed at HQ | N\A | N\A | Jerry | Shashi | Welson C. | Ethi | Evan | John H. | Lien | Hai Nguyen | PoE
Torrance system | PLT | 10 | no SSD,PSU,fan | ASY-72028-111 Rev A0 | ASY-72028-111 Rev A0 | Not Started | SGD | 0 | N\A | 3/25/20 | 4/1/20 | 4/13/20 | 4/29/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 12/23: Version -111 is with final chip. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance system | PLT | 40 | Forward | ASY-92039-111 Rev A0 | ASY-92039-111 Rev A0 | Not Started | SGD | 0 | N\A | 3/25/20 | 4/1/20 | 4/13/20 | 4/29/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 2/28: Moved PLT Build Start out to 4/1 but it's really TBD due to materials issues with China. 12/23: Version -111 is with final chip. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance system | PPLT | 4 | no SSD,PSU,fan | ASY-72028-103 Rev A0 | ASY-72028-103 Rev A0 | In-Process | SGD | 0 | N\A | 2/12/20 | 2/20/20 | 2/28/20 | 3/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 12/23: Version -111 is with final chip. 12/23: Corrected part version. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance system | PPLT | 24 | Forward | ASY-92039-103 Rev A0 | ASY-92039-103 Rev A0 | In-Process | SGD | 0 | N\A | 2/12/20 | 2/20/20 | 2/28/20 | 3/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 2/28: SMT for daughter card and adapter card done. 2/20: All materials in-house for this build. Just waitig for confirmation on start date from SGD. Likely start 2/25. 2/13: Build start moved out from 2/10 due to materials shortages. SGD now getting parts from SSJ, due to ship out 2/14. New build start date is 2/20, based on 2/12 information when parts will dock from SSJ. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-BK system | PLT | 8 | no SSD,PSU,fan | ASY-72129-102 Rev A0 | ASY-72129-102 Rev A0 | Not Started | SGD | 0 | N\A | 2/26/20 | 3/4/20 | 3/16/20 | 4/1/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 2/10: Corrected asy number version to be -102 and not -111.12/23: Version -111 is with final chip. 12/23: Corrected part number. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-BK system | PLT | 42 | Forward | ASY-92070-102 Rev A0 | ASY-92070-102 Rev A0 | Not Started | SGD | 0 | N\A | 2/26/20 | 3/4/20 | 3/16/20 | 4/1/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 2/20: Build start might take a 2-month hit from 3/4 start date due to issues getting parts from China. 2/10: Corrected asy number version to be -102 and not -111. 2/4/20: Keeping PLT start at 3/4/20. 12/23: Version -111 is with final chip. 12/23: Corrected part version. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-BK system | PPLT | 2 | no SSD,PSU,fan | ASY-72129-102 Rev A0 | ASY-72129-102 Rev A0 | In-Process | SGD | 20 | N\A | 1/31/20 | 2/7/20 | 2/20/20 | 3/10/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 12/23: Corrected part number. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-BK system | PPLT | 18 | Forward | ASY-92070-102 Rev A0 | ASY-92070-102 Rev A0 | In-Process | SGD | 20 | N\A | 1/31/20 | 2/7/20 | 2/17/20 | 3/10/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 2/20: All Woodpecker-10s, all daughter cards, and all switch cards built. 6 switch cards through ICT. Mech asy training in -porcess. 2/13: First 4 switch cards into ICT today. 2/10: SMT for switch card went from 1/27 to 2/5 and then started 2/7. SGD committed to starting mech asy Monday morning 2/17. 2/4: Build start moved from 1/27 to 2/5. 1/14: Build start in jeopardy. ICT fixture not shipped out yet because of issues. SGD's NRE not approved yet, so fixtures are not yet in place. And MEM-00306 is not available until March - trying to expedite. 12/23: Corrected part version. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS Daughtercard | P1A | 0 | PCA only | PCA-01399-02 | PCA-01399-02 | Not Started | SSJ | 15 | 6/4/19 | 2/26/20 | 3/4/20 | 3/9/20 | 3/25/20 | AOI,5DX,FLY | 2/20: Start date at risk because gave part to SGD for Torrance PPLT. Will have issue getting parts from China. B0 B52s now due late March, not early March. 2/3: Build start moved out from 1/16 to 3/4, waiting for B0 chips. (We do not want screened chips for Torr-MS - only B0.) 1/14: Build on hold because B52s have to be purged. Did not get STL2 screen at Credo. Re-start date TBD. | N\A | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS Daughtercard | P1B | 0 | PCA only | PCA-01399-02 | PCA-01399-02 | Not Started | SSJ | 0 | N\A | 3/30/20 | 4/6/20 | 4/15/20 | 4/20/20 | AOI,5DX,FLY | N\A | N\A | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS system | P1A | 15 | Forward | ASY-92067-102 | ASY-92067-102 | Not Started | SGD | 0 | N\A | 2/26/20 | 3/4/20 | 3/9/20 | 3/25/20 | AOI,5DX,FLY,FVT,ESS,BI | 2/3: Build start moved out from 1/16 to 3/4, waiting for B0 chips. (We do not want screened chips for Torr-MS - only B0.) 1/14: Build on hold because B52s have to be purged. Did not get STL2 screen at Credo. Re-start date TBD. | B1, -04 | LLucia- 8/7 Short Jericho2 Rev 04 Chip; pending allocation | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS system | P1B | 10 | Forward | ASY-92067-102 | ASY-92067-102 | Not Started | SGD | 0 | N\A | 3/30/20 | 4/6/20 | 4/15/20 | 4/20/20 | AOI,5DX,FLY,FVT,ESS,BI | N\A | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | N\A | Lorraine | Sherry | 2RU
Torrance-MS system | PLT | 6 | no SSD,PSU,fan | ASY-72123-102 | ASY-72123-102 | Not Started | SGD | 0 | N\A | 6/11/20 | 6/18/20 | 6/30/20 | 7/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS system | PLT | 44 | Forward | ASY-92067-102 | ASY-92067-102 | Not Started | SGD | 0 | N\A | 6/11/20 | 6/18/20 | 6/30/20 | 7/20/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS system | PPLT | 4 | no SSD,PSU,fan | ASY-72123-102 | ASY-72123-102 | Not Started | SGD | 20 | N\A | 5/4/20 | 5/12/20 | 5/22/20 | 6/11/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Torrance-MS system | PPLT | 16 | Forward | ASY-92067-102 | ASY-92067-102 | Not Started | SGD | 20 | 5/15/20 | 5/4/20 | 5/12/20 | 5/22/20 | 6/11/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | 2/10: Going from P1B to PPLT. P2 builds cancelled and hidden. Pulling in PPLT start from June 16 to May 12. | B1, -04 | N\A | Madeleine | Eddie | Duong N. | Manik | Cliff | Michael L. | Lorraine | Sherry | 2RU
Volstagg | P1A | 30 | PCA only | PCA-01501-01 | PCA-01501-01 | Not Started | SSJ | 10 | 2/14/20 | 3/12/20 | 3/19/20 | 3/27/20 | 4/2/20 | AOI,FLY | Deliver 6 boards to HQ prior to 27-March if possible. | N\A | N\A | Jerry | Shashi | Welson C. | Ethi | Evan | John H. | Lien | Hai Nguyen | PoE
Windy Creek (Eldridge) | P2I | 0 | N\A | PCA-01185-02 | PCA-01185-02 | In-Process | SSJ | 15 | 1/31/20 | 2/24/20 | 3/2/20 | 3/9/20 | 3/30/20 | AOI,5DX,FP | Qty 125 for Dragonfly | N\A | N\A | Mike M. | Paulmer | James M. | TBD | Matt G. | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | P1A | 8 | N\A | ASY-54996-101 | ASY-54996-101 | Not Started | SSJ | 15 | 4/8/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | P1B | 16 | N\A | ASY-54996-101 | ASY-54996-101 | Not Started | SSJ | 15 | 4/8/20 | 6/1/20 | 6/7/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | P2A | 16 | N\A | ASY-54996-102 | ASY-54996-102 | Not Started | SSJ | 15 | 7/10/20 | 7/30/20 | 8/6/20 | 8/13/20 | 9/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | P2B | 42 | N\A | ASY-54996-102 | ASY-54996-102 | Not Started | SSJ | 15 | 7/10/20 | 8/31/20 | 9/5/20 | 9/11/20 | 10/2/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | PLT | 40 | N\A | ASY-54996-103 | ASY-54996-103 | Not Started | SGD | 15 | 10/16/20 | 12/7/20 | 12/12/20 | 12/18/20 | 1/8/21 | AOI,5DX,ICT, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O | PPLT | 36 | N\A | ASY-54996-103 | ASY-54996-103 | Not Started | SGD | 15 | 10/16/20 | 11/5/20 | 11/12/20 | 11/19/20 | 12/10/20 | AOI,5DX,ICT, FVT, ESS, BI, FST, ORT | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O Riser Card | P1A | 0 | N\A | PCA-01508-01 | PCA-01508-01 | Not Started | SSJ | 15 | 4/8/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP | Qty = 152 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O Riser Card | P1B | 0 | N\A | PCA-01508-01 | PCA-01508-01 | Not Started | SSJ | 15 | 4/8/20 | 6/1/20 | 6/7/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 304 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O Riser Card | P2A | 0 | N\A | PCA-01508-02 | PCA-01508-02 | Not Started | SSJ | 15 | 7/10/20 | 7/30/20 | 8/6/20 | 8/13/20 | 9/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 304 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-O Riser Card | P2B | 0 | N\A | PCA-01508-02 | PCA-01508-02 | Not Started | SSJ | 15 | 7/10/20 | 8/31/20 | 9/5/20 | 9/11/20 | 10/2/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 798 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | P1A | 8 | N\A | ASY-5xxxx-101 | ASY-5xxxx-101 | Not Started | SSJ | 15 | 4/8/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | P1B | 16 | N\A | ASY-5xxxx-101 | ASY-5xxxx-101 | Not Started | SSJ | 15 | 4/8/20 | 6/1/20 | 6/7/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | P2A | 16 | N\A | ASY-5xxxx-102 | ASY-5xxxx-102 | Not Started | SSJ | 15 | 7/10/20 | 7/30/20 | 8/6/20 | 8/13/20 | 9/3/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | P2B | 42 | N\A | ASY-5xxxx-102 | ASY-5xxxx-102 | Not Started | SSJ | 15 | 7/10/20 | 8/31/20 | 9/5/20 | 9/11/20 | 10/2/20 | AOI,5DX,FP, FVT, ESS, BI | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | PLT | 40 | N\A | ASY-5xxxx-103 | ASY-5xxxx-103 | Not Started | SGD | 15 | 10/16/20 | 12/7/20 | 12/12/20 | 12/18/20 | 1/8/21 | AOI,5DX,ICT, FVT, ESS, BI, FST | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q | PPLT | 36 | N\A | ASY-5xxxx-103 | ASY-5xxxx-103 | Not Started | SGD | 15 | 10/16/20 | 11/5/20 | 11/12/20 | 11/19/20 | 12/10/20 | AOI,5DX,ICT, FVT, ESS, BI, FST, ORT | N\A | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q Riser Card | P1A | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SSJ | 15 | 4/8/20 | 5/1/20 | 5/8/20 | 5/15/20 | 6/5/20 | AOI,5DX,FP | Qty = 152 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q Riser Card | P1B | 0 | N\A | PCA-01309-03 | PCA-01309-03 | Not Started | SSJ | 15 | 4/8/20 | 6/1/20 | 6/7/20 | 6/12/20 | 7/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 304 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q Riser Card | P2A | 0 | N\A | PCA-01309-04 | PCA-01309-04 | Not Started | SSJ | 15 | 7/10/20 | 7/30/20 | 8/6/20 | 8/13/20 | 9/3/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 304 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Wolverine-Q Riser Card | P2B | 0 | N\A | PCA-01309-04 | PCA-01309-04 | Not Started | SSJ | 15 | 7/10/20 | 8/31/20 | 9/5/20 | 9/11/20 | 10/2/20 | AOI,5DX,FP, FVT, ESS, BI | Qty = 798 | N\A | N\A | Mike M. | Dave M. | James M. | Nguyen | Kash | Rohit K. | Attiya | Min Guo | Denali
Woodleaf switch card | P1A | 0 | PCA only | PCA-01439-01 | PCA-01439-01 | Not Started | SSJ | 15 | 2/10/20 | 2/25/20 | 3/3/20 | 3/6/20 | 3/13/20 | AOI,5DX,FLY | 2/10: Qty. 8 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf switch card | P1B | 0 | PCA only | PCA-01439-01 | PCA-01439-01 | Not Started | SSJ | 0 | N\A | 3/25/20 | 4/1/20 | 4/8/20 | 4/24/20 | AOI,5DX,FLY | 2/10: Qty. 16 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf switch card | P2A | 0 | PCA only | PCA-01439-02 | PCA-01439-02 | Not Started | SSJ | 15 | 5/18/20 | 6/2/20 | 6/9/20 | 6/12/20 | 6/26/20 | AOI,5DX,FLY | 2/10: Qty. 22 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf switch card | P2B | 0 | PCA only | PCA-01439-02 | PCA-01439-02 | Not Started | SSJ | 0 | N\A | 7/8/20 | 7/15/20 | 7/22/20 | 8/5/20 | AOI,5DX,FLY | 2/10: Qty. 28 | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | P1A | 8 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SSJ | 15 | 2/10/20 | 3/9/20 | 3/17/20 | 3/20/20 | 3/27/20 | AOI,5DX,FLY | 2/24: Build start moving out from 3/3 to 3/17 because fabs not docking until 3/16. 2/10: Reduced qty. from 15 to 8, so that parts can be freed up for Torrance, which is higher priority. 1/30: Increased P1A from 7 to 15. Moved P1A fabout from 1/15 to 2/20. 1/6/20: Updated fabout to be 1/15/20. | N\A | 2/24: LLucia Fab Dock Date is 3/16 2/21: LLucia- Sheet Metal shipping from Asia on 2/28 HSK's scheduled to dock on 3/20 | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | P1B | 16 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SSJ | 0 | N\A | 4/7/20 | 4/16/20 | 4/23/20 | 5/14/20 | AOI,5DX,FLY | 1/30: Inc. qty. from 14 to 16, and eliminated Reverse config. because supplies will not be ready. | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | P2A | 22 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SSJ | 15 | 6/1/20 | 6/15/20 | 6/22/20 | 6/25/20 | 7/16/20 | AOI,5DX,FLY,FVT | 2/12: First time with B0 chip. 2/10: Inc. qty. from 14 to 22. 1/30: Inc. qty,. from 10 to 14. | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | P2B | 4 | Reverse | ASY-92133-101 | ASY-92133-101 | Not Started | SSJ | 0 | N\A | 7/30/20 | 8/6/20 | 8/13/20 | 9/2/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 1/30: P2B is first time for Reverse config. | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | P2B | 24 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SSJ | 0 | N\A | 7/30/20 | 8/6/20 | 8/13/20 | 9/2/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | 2/10: Inc. Forward from 18 to 24. | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PLT | 4 | no SSD,PSU,fan | ASY-72154-101 | ASY-72154-101 | Not Started | SGD | 0 | N\A | 11/10/20 | 11/18/20 | 12/3/20 | 12/21/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PLT | 6 | Reverse | ASY-92133-101 | ASY-92133-101 | Not Started | SGD | 0 | N\A | 11/10/20 | 11/18/20 | 12/3/20 | 12/21/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PLT | 40 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SGD | 30 | 9/21/20 | 11/10/20 | 11/18/20 | 12/3/20 | 12/21/20 | AOI,5DX,ICT,FVT,ESS,BI,FST | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PPLT | 2 | no SSD,PSU,fan | ASY-72154-101 | ASY-72154-101 | Not Started | SGD | 0 | N\A | 9/21/20 | 9/28/20 | 10/8/20 | 10/26/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PPLT | 2 | Reverse | ASY-92133-101 | ASY-92133-101 | Not Started | SGD | 0 | N\A | 9/21/20 | 9/28/20 | 10/8/20 | 10/26/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU
Woodleaf system | PPLT | 16 | Forward | ASY-92132-101 | ASY-92132-101 | Not Started | SGD | 20 | 8/27/20 | 9/21/20 | 9/28/20 | 10/8/20 | 10/26/20 | AOI,5DX,ICT,FVT,ESS,BI,FST,ORT | N\A | N\A | N\A | Madeleine | Jayagopal | Duong N. | Vipul | Cliff | Michael L. | Lorraine | Sherry | 2RU